## Team Members
Enter the First Name of Each Team Member | HOW TO USE: | 1. File Menu --> Make a copy
Hamad Almoqbel |  | 2. Save to one team member's Google drive
Abdulrahman Alafif |  | 3. Share file with other team members
Ziyad Al-Rushud |  | 4. Edit First Names on this tab
Waleed Drweesh |  | 5. Add your team name to the name of this document
Mashhour aleid |  | 6. For each sprint, duplicate the sprint template and change the start date
Abdurabu Saleh
DOCUMENT HISTORY
| 2017-09-20 | Created by Justin Sybrandt (http://sybrandt.com/post/google-slides-agile/)
| 2019-03-23 | Modified by Susanne Sherba for use in COMP 3381 (Software Engineering I)

## Product Backlog
Sprint Number | User Story ID | User Story Title | Brief Description | Additional Information | Priority | Status
1 | S1 | Initial Setup and UI Design | As a player, I want a visually appealing initial screen with placeholders for each letter, so I can easily understand the game's layout. |  | 1-high | Done
1 | S2 | User Input and Validation | As a player, I want to input my guesses using a user-friendly interface and receive feedback on the validity of my input. |  | 1-high | Done
1 | S3 | Checking the Guess and Incorrect Guesses | As a player, I want the game to accurately check my guessed letters and keep track of incorrect guesses, providing a visual representation of incorrect attempts. |  | 1-high | Done
| S4 | Game Loop, Win/Loss Conditions | As a player, I want the game to continue until I win or lose, and I want clear conditions for both scenarios. Additionally, I want the entire word revealed at the end of the game. |  | 1-high | Done
| S5 | Score Tracking | As a player, I want my performance tracked, with a visible score displayed at the end of each game. |  | 2-medium | Done
| S6 | Different Challenge for each level | As a player, I want the option to choose word categories to add variety to the game. |  | 1-high | Done
| S7 | Player Name Display | As a player, I want the option to play in a multiplayer mode, with the ability to see the names of other players. |  | 2-medium | Done
| S9 | UI Enhancement | As a player, I want an aesthetically pleasing and responsive user interface to enhance my overall gaming experience. |  | 1-high | Done
| S10 | Sound Effects | As a player, I want the game to include sound effects for correct and incorrect guesses, as well as background music during gameplay. |  | 3-low | Done
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do
[5 empty] | 3-low | To Do

## Sprint 1
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S1 | Set up a new Flutter project. | 4 | 4 | Hamad Almoqbel | Done |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 48 | 48
S1 | Design the initial screen with placeholders for each letter. | 8 | 5 | Abdulrahman Alafif | Done |  | Start Date: | 2019-03-30 | Hamad Almoqbel | 9 | 9 | 100% | #NAME? | 0 | 0 | #NAME? | 44.5714
S2 | Implement user input for guessing a letter using Flutter widgets. | 7 | 6 | Waleed Drweesh | Done |  | Sprint Length | 14 | Abdulrahman Alafif | 8 | 8 | 100% | #NAME? | 0 | 0 | #NAME? | 41.1429
S2 | Validate input and update the UI accordingly. | 9 | 5 | Ziyad Al-Rushud | Done |  | Hours Per Day: | 3.4286 | Ziyad Al-Rushud | 9 | 9 | 100% | #NAME? | 0 | 0 | #NAME? | 37.7143
S3 | Compare the guessed letter with the letters in the word. | 8 | 6 | Mashhour aleid | Done |  |  |  | Waleed Drweesh | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 34.2857
S3 | Update the display to reveal correctly guessed letters | 5 | 5 | Hamad Almoqbel | Done |  |  |  | Mashhour aleid | 8 | 8 | 100% | #NAME? | 0 | 0 | #NAME? | 30.8571
S3 | Keep track of correct guesses. | 7 | 7 | Abdurabu Saleh | Done |  |  |  | Abdurabu Saleh | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 27.4286
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 24
[5 empty] | To Do |  |  |  | Total: | 48 | 48 | 100% | #NAME? | 0 | 0 | #NAME? | 20.5714
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 17.1429
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 13.7143
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 10.2857
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 6.8571
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 3.4286
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 2
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S4 | Implement a loop that continues until the game is won or lost. | 9 | 8 | Hamad Almoqbel | Done |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 50.5 | 50.5
S4 | Provide an option to restart the game. | 7 | 7 | Abdurabu Saleh | Done |  | Start Date: | 2019-03-30 | Hamad Almoqbel | 9 | 9 | 100% | #NAME? | 0 | 0 | #NAME? | 46.8929
S4 | Define conditions for winning or lossing | 8 | 9 | Ziyad Al-Rushud | Done |  | Sprint Length | 14 | Abdulrahman Alafif | 8 | 8 | 100% | #NAME? | 0 | 0 | #NAME? | 43.2857
S4 | Display appropriate messages when the game concludes. | 8.5 | 7 | Mashhour aleid | Done |  | Hours Per Day: | 3.6071 | Ziyad Al-Rushud | 8 | 8 | 100% | #NAME? | 0 | 0 | #NAME? | 39.6786
S5 | Implement a scoring system. | 5 | 6 | Waleed Drweesh | Done |  |  |  | Waleed Drweesh | 10 | 10 | 100% | #NAME? | 0 | 0 | #NAME? | 36.0714
S5 | Display the user's score at the end of each game. | 5 | 5 | Waleed Drweesh | Done |  |  |  | Mashhour aleid | 8.5 | 8.5 | 100% | #NAME? | 0 | 0 | #NAME? | 32.4643
S6 | Introduce certain Letters for each leavel. | 8 | 7 | Abdulrahman Alafif | Done |  |  |  | Abdurabu Saleh | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 28.8571
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 25.25
[5 empty] | To Do |  |  |  | Total: | 50.5 | 50.5 | 100% | #NAME? | 0 | 0 | #NAME? | 21.6429
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 18.0357
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 14.4286
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 10.8214
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 7.2143
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 3.6071
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 1.1546e-14
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")

## Sprint 3
User Story ID | Task | Expected Hours | Actual Hours | Person | Status | Date Completed | [6 empty] | Chart Dates | Completed Hours On Date | Current Completed Work | Current Remaining Work | Ideal Remaining Work
S7 | Display the current player's name. | 7 | 5 | Abdurabu Saleh | Done |  | Sprint Number: | 0 | Person | Hours Assigned | Hours Completed | Percentage Complete | 2019-03-30 | 0 | 0 | 43 | 43
S9 | Enhance the overall look and feel of the game interface. | 10 | 11 | Waleed Drweesh | Done |  | Start Date: | 2019-03-30 | Hamad Almoqbel | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 39.9286
S9 | Add images for a more engaging user experience. | 7 | 8 | Hamad Almoqbel | Done |  | Sprint Length | 14 | Abdulrahman Alafif | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 36.8571
S10 | Add sound effects | 6 | 7 | Ziyad Al-Rushud | Done |  | Hours Per Day: | 3.0714 | Ziyad Al-Rushud | 6 | 6 | 100% | #NAME? | 0 | 0 | #NAME? | 33.7857
S4 | Timer decision that the player lost or not. | 6 | 7 | Mashhour aleid | Done |  |  |  | Waleed Drweesh | 10 | 10 | 100% | #NAME? | 0 | 0 | #NAME? | 30.7143
S1 | Add options button with some features | 7 | 7 | Abdulrahman Alafif | Done |  |  |  | Mashhour aleid | 6 | 6 | 100% | #NAME? | 0 | 0 | #NAME? | 27.6429
[5 empty] | To Do |  |  |  | Abdurabu Saleh | 7 | 7 | 100% | #NAME? | 0 | 0 | #NAME? | 24.5714
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 21.5
[5 empty] | To Do |  |  |  | Total: | 43 | 43 | 100% | #NAME? | 0 | 0 | #NAME? | 18.4286
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 15.3571
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 12.2857
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 9.2143
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 6.1429
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 3.0714
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
[5 empty] | To Do | [7 empty] | #NAME? | 0 | 0 | #NAME? | 0
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
To Do
Formulas:
Current Remaining Work = IF([Chart Dates] <= TODAY(), M10-[Current Completed Work], "")